## Viability C'land
ALBION STREET CROWLAND
22 New homes
Private |  | House Type | No. | GIA m2 | Total GIA m2 | Sale Price | Total sale price GDV-predicted | Plot no.
Type 1 |  | 3 bed linked with garage | 2 | 110 | 220 | 250000 | 500000 | 20,21
Type 2 |  | 3 bed detached with garage | 2 | 100 | 200 | 250000 | 500000 | 3,4
Type 3 |  | 3 bed semi | 4 | 86 | 344 | 205000 | 820000 | 11-14
Type 5 |  | 3 bed semi | 6 | 106 | 636 | 240000 | 1440000 | 15-20
Type 6 |  | 3 bed linked with garage | 2 | 115 | 230 | 250000 | 500000 | 1,2
Type 7 |  | 2 bed semi/terrace | 3 | 80 | 240 | 175000 | 525000 | 5,6,7
|  |  | 19 |  | 1870
Affordable |  | House Type | No. | GIA m2 | Total Gia m2 | Sale Price | Total sale price | Plot no.
Type 1 |  | 1 bed | 2 | 55 | 110 |  |  | 8
Type 2 |  | 2 bed | 1 | 75 | 75 |  |  | 9,10
|  |  | 3 |  | 185
|  | TOTAL UNITS: | 22 | Total m2: | 2055
COST DESCRIPTION | NOTES
22 units
Land |  |  | inc stamp | 537000 |  | ACTUAL SALES
Build costs |  |  |  | 2722875 |  | Plot | Sales | Sales dates
Services | inc diverting electric main left on site by LCC |  | Water/Gas/Electric | 90000 |  | 1 | 250000 | 12.3.21
Adobatble Rd/Footpath |  |  |  | 120000 | 310000 | 2 | 255000 | 11.3.21
S104 Drainage | inc de watering |  |  | 190000 |  | 3 | 255000 | 27.9.21
Extra S278 works |  |  |  | 7000 |  | 4 | 255000 | 8.10.21
Planning achitect |  |  |  | 25000 |  | 5 | 180000 | 3.8.21
application |  |  |  | 8000 |  | 6 (20% off) | 144000 | 3.8.21
Building regs |  |  |  | 16000 |  | 7 | 180000 | 24.6.21
10 year guarnatee |  |  |  | 37400 |  | 8 | 232500 | 15.8.22
structural engineer |  |  |  | 8500 |  | 9
Building control |  |  |  | 13200 |  | 10
Drainage design |  |  |  | 12000 |  | 11 | 210000 | 3.9.21
Site set up, cabins , water, electric |  |  |  | 5000 |  | 12 | 210000 | 6.8.21
consumables on site, skips, wc , electric, water , telephone , internet |  |  |  | 24000 |  | 13 | 210000 | 5.11.21
office and over heads |  |  |  | 25000 |  | 14(20% off) | 176000 | 29.10.21
costs associated with Linc county council/ HE |  | SOCIAL HOUSES PAYMENT, C'FIELD COSTS |  | 20000 |  | 15 | 245000 | 16.12.21
Viabilty study |  |  |  | 4500 |  | 16 | 245000 | 22.12.21
LCC road fees development fees |  |  |  | 9000 |  | 17 | 245000 | 3.9.21
[6 empty] | 18 | 245000 | 17.9.21
[6 empty] | 19 | 245000 | 28.7.21
[6 empty] | 20 | 245000 | 31.8.21
[6 empty] | 21 | 275000 | 22.11.21
[6 empty] | 22 | 255000 | 8.10.21
[6 empty] | Total sales: | 4557500
|  | Actual Scheme costs: |  | 3874475
|  | Actual Sales (GDV): |  | 4557500
|  | Profit from sales: |  | 683025
|  | Sales Fees: |  | 45575
|  | Solictor fees: |  | 19800
|  | Bank fees: |  | 75000
140375
|  | Profit: |  | 542650 | 11.91%
New Plots Costs
Site set up |  | 9000 |  | office , store/canteen , wc , water, electric
Sales
Plot 9 105m2 | build cost | 142056.6 | 239000
Plot 3 90m2 | build cost | 119056.96 | 205000
Plot 4 90m2 | build cost | 119056.96 | 205000
Planning |  | 6000
B.regs |  | 6000
Flood risk |  | 750
10 year Guarantee |  | 6000
Structural engineer |  | 3000
Consumables on site |  | 10000 |  | telephone , internet , water , elec
LCC / drop kerbs |  | 4000
Viability study SHDC |  | 1750
Churchfield costs associated with viability |  | 3750
Services |  | 12000 | gas , water , electric , mains
Bank surveyor / monitoring |  | 6400 |  | 8 x £800 monitoring / draw down visits
Site manager / surveyor |  | 45000
Development costs |  | 493820.52
Contingency | 7.5% | 37036.539
Total build costs: |  | 530857.059
Sales total: |  |  | 649000
Profit from sales: |  | 118142.941
Sales Fees: |  | 7788 | 1.2%
Solictors fees |  | 3000
Bank/Finance Fees: |  | 28000
38788
Profit: |  | 79354.941
Profit on 22no. Initails scheme |  | 542650
Profit on 3no. Additional dwellings |  | 79354.941
622004.941
Total sales 25no. Houses |  | 5206500
Profit for 25no. Houses |  | 622004.941 | 11.95%

## Sheet1
Land off Boston Road | House Type F
Gosberton | 3 Bed Semi Detached | Drawing numbers: |  | 038927.1005C | Layout plans
Plot numbers: 10-13, 16,17 |  |  |  | 038927.2005D | Elevations
|  |  |  | 038927.3005C | Sections
|  |  |  | 038927.4005B | Horizontal Setting Out
Item | Description | Quantity | Unit | Rate | Cost | Notes/sub contractor
Strip Top soil | Strip and keep on site for later use |  |  | sum | 1500 | Inc muck away |  | Groundworks/Sub Structure
Set out | 2 visits | 2 | item | 200 | 400 | Engineer
Dig foundation | 750mm (w) x 1000mm (d) Keep spoil on site | 60 | m3 | 70 | 4200 | Inc muck away
Concrete Foundation | 500mm (d) x 750mm(w) | 32 | m3 | 170 | 5440
Sub-Structure blockwork | 2 course 7n 300mm trench blocks. Ext walls only | 11.25 | m2 | 70 | 787.5
Sub-Structure blockwork | 4 course 100mm 7N Dense Concrete Block. Ext walls | 56 | m2 | 50 | 2800
Sub-Structure blockwork | 4 course 100mm 7n laid flat | 35 | m2 | 50 | 1750
Backfill | Back with spoil. Level perimeter with recycled material |  |  |  | 1000
Lintels over drainage | Conc lintels over drainage | 12 | no. | 75 | 900
Plot drainage | FW/SW - 100mm dia plastic. Surround 10mm gravel |  |  | sum | 3500
Water/elec duct | 100mm blue -water, 50mm black electric |  |  |  | 360
Beam and block floor | 150mm deep concrete floor beams infill - 100mm blocks | 90 | m2 | 55 | 4950
Brickwork below DPC | 150mm (2 course face bricks) | 19 | m2 | 129.2 | 2454.8 |  | 30042.3
100mm DPC | Ext & Int skin | 110 | Lm | 6 | 660 |  |  | Super Structure
450mm DPC | Over lintels/boxes/vents | 60 | Lm | 6 | 360
Form cavity/wall ties | HRT4 or similar housing tie/party wall ties | 260 | m2 | 10 | 2600
3 phase meter box | Electric meter box | 2 | no. | 150 | 300
Super structure - Face brickwork | Half Bond bucket handle joint. 102.5mm outer skin | 196 | m2 | 129.96 | 25472.16
Super structure- Ext Blockwork | 100mm celcons aircrete or similar. 100mm inner skin | 196 | m2 | 47.5 | 9310
Internal blockwork | 100mm celcons or similar. GF walls only | 147 | m2 | 47.5 | 6982.5 | Inc party wall EWM - 22
Lintels | Cavity - hi therm plus internals | 1 | no. | item | 2164
Cavity Insulation | 100mm Dri - Therm 32 | 260 | m2 | 34 | 8840
1st floor joists | 225mm deep posi joists | 1 | no. | item | 4200
1st floor deck | 22mm peel clean egger board or similar | 84 | m2 | 22 | 1848
1st floor deck | Glue/adhesive | 12 | no. | 8.95 | 107.4
Roof trusses | Roof trusses to house. Lifted on with crane | 1 | no. | sum | 5000 | Inc crane
Roof coverings/gutters | Breathable membrane. Batton. Concrete tiles | 1 | no. | sum | 8000
Black plastic rw goods
Scaffold | Independent with 1no. Loading bay inc Trad system | 1 | no. | sum | 6000 |  | 81844.06
Windows | UPVC - colour - see plot schedule. | 1 | no. | sum | 9450 |  |  | 1st Fix & Plastering
Ground floor insulation & screed | 175mm kingspan or similar. 50mm pump screed | 90 | m2 | 65 | 5850
Concrete garage floor | 100mm thick concrete. Tamp finish | 0 | m3 | 150 | 0
1st fix carpentry | 1st floor studwork - 47 x 100 timber
Door liners
138mm - studwork
155mm blockwork
MDF window baord 25mm x 294mm
Window baord channel
Window board bracket
Straight flight stairs
Boxing soil pipes
| Pre formed porch canopy (flat) |  |  |  |  | Over front door
1st fix carpentry (labour) | Labour element - joists/roof/1st fix |  |  |  | 10400
Plastering | 15mm board to ceilings. 12.5mm dot & Dab walls. Skim | 1 | no. | sum | 15000
Plumbing | 1st and 2nd fix. Inc air source heat pump. |  |  | sum | 28000
Fit bathroom/en suite/kitchen/utility. Inc Mastic
Electrics | 1st and fix |  |  | sum | 8000 |  | 76700
Outside lights | Supply outside lights and bulbs | 10 | no. | 20 | 200 |  |  | 2nd Fix & Landscaping
Bathrooms |  |  |  |  | 4000
En - Suites | Fitting included in plumbing above
W/C ground floor |  |  |  |  | 800
2nd Fix carpenrty | Doors-Dordogne smooth or similar.
Handles-Newington packs or similar
Skirting MDF primed Burford or similar 96mm
Archtrave MDF primed burford or similar 45mm
Slatted shelving in A/C. 2x1 plained
Boxings in MDF 18mm
MDF 18mm wardrobe shelf
2nd fix Carpenrty Labour | Labour element - fit doors skirting etc |  |  |  | 8400
Loft hatch | Pre formed hinged & insulated | 2 | no. | 120 | 240
Loft Insulation | 300mm total in 2no. Layers | 90 | m2 | 25 | 2250
Kitchen | Units, appliances, worktops. Supply/fit |  |  |  | 12000
Tiling | Bathroom/ensuite/wc spalshabck | 50 | m2 | 55 | 2750
Paint Decorate | Throughout building. |  |  |  | 6500
Externals | Paving
Fence -1.8m closeboard
Driveway - permebale tarmac
Turf - rear gardens
Path edgings
Gate
| Shrubs |  |  |  | 13000
Clean | Build clean on practical completion | 2 | no. | 400 | 800
Snagging |  | 2 | no. | 500 | 1000
Prelims | Skips | 10 | no. | 300 | 3000 |  | 54940
Floorings | Carpets & Vinyl (not included in sale) |  |  |  | 6000
TOTAL FOR HOUSE: |  |  |  |  | 243526.36 |  | 243526.36
TOTAL FOR GARAGE:
GRAND TOTAL: |  |  |  |  | 243526.36
TOTAL m2: |  |  | m2 |  | 180 | m2
Cost per m2: | Including single garage |  |  |  | 1352.9242