## Summary
Housebuild Viability Appraisal
1) Groundworks (Plot Development)
Excavate & Concrete Foundations | 70 | Plots | 18000 | 1260000 | 70 | Plots | 18000 | 1260000 | Rates provided suggest this is close to average
Brickwork to DPC | 49 | Garages | 6000 | 294000 | 49 | Garages | 6000 | 294000 | Rates provided suggest this is close to average
Floor Beams & Slab Construction |  |  | Inc |  |  |  | Inc
Slab Concrete |  |  | Inc |  |  |  | Inc
Plot Drainage |  |  | Inc |  |  |  | Inc
Plot Service Ducts |  |  | Inc |  |  |  | Inc
2) Brickwork Superstructure
House
Brickwork Labour | 595000 | Bricks | 0.7 | 416500 | 595000 | Bricks | 0.7 | 416500 | £42/m2 is acceptable
Blockwork Labour | 10908 | Blocks | 18 | 196344 | 10908 | Blocks | 18 | 196344 | Assume this is £/m2; acceptable
Facing Bricks Material | 595000 | Bricks | 0.55 | 327250 | 595000 | Bricks | 0.55 | 327250
Blockwork Material | 10908 | Blocks | 15 | 163620 | 10908 | Blocks | 15 | 163620 | Assume this is £/m2; acceptable
Mortar | 375 | t | 267.75 | 100406.25 | 375 | t | 267.75 | 100406.25
Wastage | 12 | % | 1204120.25 | 144494.43 | 10 | % | 1204120.25 | 120412.025 | This is our final position
Steels | 70 | Plots | 650 | 45500 | 70 | Plots | 650 | 45500 | Supply and install; ok
Stone Cills | 70 | Plots | 450 | 31500 | 70 | Plots | 450 | 31500 | Supply and install; ok
Cavity Insulation | 70 | Plots | 850 | 59500 | 70 | Plots | 850 | 59500 | Supply and install; ok
1st Floor Joists | 70 | Plots | 1900 | 133000 | 70 | Plots | 1900 | 133000 | Supply and install; ok
2nd Floor Joists | 31 | Plots | 1900 | 58900 | 31 | Plots | 1900 | 58900 | Supply and install; ok
Roof Trusses | 39 | Plots | 2450 | 95550 | 39 | Plots | 2450 | 95550 | Supply and install; ok
Roof Trusses (Room in roof) | 31 | Plots | 6500 | 201500 | 31 | Plots | 6500 | 201500 | Supply and install; ok
Fascia & Soffit | 70 | Plots | 650 | 45500 | 70 | Plots | 650 | 45500 | Supply and install; ok
Garages
Brickwork Labour | 56595 | Bricks | 0.7 | 39616.5 | 56595 | Bricks | 0.7 | 39616.5 | As above
Blockwork Labour | 1038 | Blocks | 18 | 18684 | 1038 | Blocks | 18 | 18684 | As above
Facing Bricks Material | 56595 | Bricks | 0.55 | 31127.25 | 56595 | Bricks | 0.55 | 31127.25 | As above
Blockwork Material | 1038 | Blocks | 15 | 15570 | 1038 | Blocks | 15 | 15570 | As above
Mortar | 103 | t | 267.75 | 27578.25 | 103 | t | 267.75 | 27578.25 | As above
Steels | 49 | Plots | 185 | 9065 | 49 | Plots | 185 | 9065 | As above
3) Scaffolding
Scaffolding House | 70 | Plots | 2750 | 192500 | 70 | Plots | 2750 | 192500 | Supply and install; ok
Scaffolding Garages | 49 | Garages | 1050 | 51450 | 49 | Garages | 1050 | 51450 | Supply and install; ok
Safety Decking | 70 | Plots | 850 | 59500 | 70 | Plots | 850 | 59500 | Supply and install; ok
4) Roof Tiling £ - £ -
Roof Tiling House | 70 | Plots | 3780 | 264600 | 70 | Plots | 3780 | 264600 | Supply and install; ok
Roof Tiling Garage | 49 | Garages | 1240 | 60760 | 49 | Garages | 1240 | 60760 | Supply and install; ok
5) Windows & Doors £ - £ -
UPVC Windows & Doors | 70 | Plots | 4818.18 | 337272.6 | 70 | Plots | 4818.18 | 337272.6 | Supply and install; ok
6) Joinery Works
1st Fix | 70 | Plots | 4500 | 315000 | 70 | Plots | 3500 | 245000 | This is our final position
2nd Fix | 70 | Plots | 5500 | 385000 | 70 | Plots | 3450 | 241500 | Agreed to revised rates
Final Fix | 70 | Plots | 1200 | 84000 | 70 | Plots | 675 | 47250 | Agreed to revised rates
Canopies 70 | 70 | Plots | 650 | 45500 | 70 | Plots | 650 | 45500
|  |  |  | 0 |  |  |  | 0
6) Plumbing & Heating |  |  |  | 0 |  |  |  | 0
1st Fix | 70 | Plots | 3443.97 | 241077.9 | 70 | Plots | 12340.6143 | 863843 | Order value is 863,843 exc sanitaryware
2nd Fix | 70 | Plots | 4305.93 | 301415.1 | 70 | Plots |  |  | Inc above
Final Fix | 70 | Plots | 405.88 | 28411.6 | 70 | Plots |  |  | Inc above
ASHP | 70 | Plots | 4547.79 | 318345.3 | 70 | Plots |  |  | Inc above
Sanitaryware | 70 | Plots | 1167.78 | 81744.6 | 70 | Plots | 1167.78 | 81744.6 | Supply and install; ok
6) Electrical
1st Fix | 70 | Plots | 1749.43 | 122460.1 | 70 | Plots | 1749.43 | 122460.1 | Supply and install; ok
2nd Fix | 70 | Plots | 1749.43 | 122460.1 | 70 | Plots | 1749.43 | 122460.1 | Supply and install; ok
Final Fix | 70 | Plots | 245 | 17150 | 70 | Plots | 245 | 17150 | Supply and install; ok
ASHP | 70 | Plots | 152.5 | 10675 | 70 | Plots | 152.5 | 10675 | Supply and install; ok
Car Chargers | 70 | Plots | 427.55 | 29928.5 | 70 | Plots | 427.55 | 29928.5 | Supply and install; ok
Garages | 47 | Garages | 185 | 8695 | 47 | Garages | 185 | 8695 | Supply and install; ok
7) Plastering
Boarding & Skimming works | 70 | Plots | 7939.76 | 555783.2 | 70 | Plots | 8544.98 | 598148.6 | Quotation received
8) Painting & Decorating
Painting & Decorating | 70 | Plots | 2577.79 | 180445.3 | 70 | Plots | 2504.1571 | 175291 | Order value is £175,291
9) Loft & Cavity Insulation
Loft Insulation | 70 | Plots | 650 | 45500 | 70 | Plots | 650 | 45500 | Acceptable
Cavity Insulation | 70 | Plots | 950 | 66500 | 70 | Plots |  | 0 | Cavity insulation included above
10) Kitchens
Kitchen & Appliances (Supply & Fit) | 70 | Plots | 3102.81 | 217196.7 | 70 | Plots | 3102.81 | 217196.7 | Acceptable
11) Wall Tiling
Wall Tiling (Tiling to shower enclosures, splashbacks, baths) | 70 | Plots | 650 | 45500 | 70 | Plots | 600 | 42000 | Order value is £42,000
12) Mastic Sealant
Mastic Sealant (Windows Internal & External, Skirts, Sanitaryware) | 70 | Plots | 420 | 29400 | 70 | Plots | 420 | 29400 | Supply and install; ok
13) Garage Doors
51 Plots | 51 | Garages | 325 | 16575 | 51 | Garages | 607.84 | 30999.84 | Quotation received
13) Cleaning
Builders Clean, Pre-Paint Clean, Sparkle | 70 | Plots | 380 | 26600 | 70 | Plots | 380 | 26600 | Acceptable
13) Floor Finishes
Carpets throughout | 70 | Plots | 2480 | 173600 | 70 | Plots | 2480 | 173600 | Acceptable
14) Misc Housebuild Specifcs
Blinds | 70 | Plots | 200 | 14000 | 70 | Plots | 200 | 14000 | Supply and install; ok
Curtain Poles | 70 | Plots | 250 | 17500 | 70 | Plots | 250 | 17500 | Supply and install; ok
Door Numbers | 70 | Plots | 30 | 2100 | 70 | Plots | 30 | 2100 | Supply and install; ok
Towel Rads | 70 | Plots | 350 | 24500 | 70 | Plots | 350 | 24500 | Supply and install; ok
Snagging | 70 | Plots | 500 | 35000 | 70 | Plots | 500 | 35000 | Supply and install; ok
|  |  | Sub-Total | 8243351.68 |  |  | Sub-Total | 7925248.315
Abnormals & Infrastucture
Site Preparation / Demolition / Remediation Works
Topsoil Strip / Site Strip | 8500 | m² | 5 | 42500 | 8500 | m² | 5 | 42500 | Rate is fine
Cut & Fill | 10500 | m³ | 6.5 | 68250 | 10500 | m³ | 6.5 | 68250 | Rate is fine
Roads & Sewers
Enabling works (site set-up / PC role) | 16 | Weeks | 2500 | 40000 | 16 | Weeks | 2500 | 40000 | As an allowance this is acceptable
Notices - S50 | 3 | Nr | 1050 | 3150 | 3 | Nr | 1050 | 3150 | As an allowance this is acceptable
Traffic Management for Off-site works | 3 | Item | 4500 | 13500 | 3 | Item | 4500 | 13500
Off-site outfall connection | 1 | Item | 12500 | 12500 | 1 | Item | 12500 | 12500
Surface water sewers | 450 | m | 775 | 348750 | 450 | m | 250 | 112500 | This is our final position
Foul Sewers | 328 | m | 675 | 221400 | 328 | m | 250 | 82000 | This is our final position
SW Manholes | 24 | Nr | 2500 | 60000 | 24 | Nr | 2500 | 60000 | As an allowance this is acceptable
FW Manholes | 18 | Nr | 2400 | 43200 | 18 | Nr | 2400 | 43200 | As an allowance this is acceptable
Gullies & House Connections | 21 | Item | 1850 | 38850 | 21 | Item | 1200 | 25200 | Revised rate accepted
Roads & Sewers - Remainder - John Mason Groundworks Order
Preliminaries | 1 | Item | 17000 | 17000 | 1 | Item | 17000 | 17000 | All as order
Foul Sewers | 1 | Item | 4848.25 | 4848.25 | 1 | Item | 4848.25 | 4848.25 | All as order
Foul Manholes | 1 | Item | 8301.14 | 8301.14 | 1 | Item | 8301.14 | 8301.14 | All as order
Foul Pump Station Remedial Works | 1 | Item | 10663.95 | 10663.95 | 1 | Item | 10663.95 | 10663.95 | All as order
Foul Pump Station | 1 | Item | 39324.1 | 39324.1 | 1 | Item | 39324.1 | 39324.1 | All as order
Rising Main Foul | 1 | Item | 11681.7 | 11681.7 | 1 | Item | 11681.7 | 11681.7 | All as order
Rising Main Connection Works into extg manhole | 1 | Item | 26755.4 | 26755.4 | 1 | Item | 26755.4 | 26755.4 | All as order
Storm Sewers | 1 | Item | 8322.67 | 8322.67 | 1 | Item | 8322.67 | 8322.67 | All as order
Storm Manholes | 1 | Item | 46475.14 | 46475.14 | 1 | Item | 46475.14 | 46475.14 | All as order
Culvert Works | 1 | Item | 54566.87 | 54566.87 | 1 | Item | 54566.87 | 54566.87 | All as order
Attenuation Crate | 1 | Item | 209536.97 | 209536.97 | 1 | Item | 209536.97 | 209536.97 | All as order
Attentuation Pond | 1 | Item | 14191.82 | 14191.82 | 1 | Item | 14191.82 | 14191.82 | All as order
Swales (Road 1) | 1 | Item | 35609.32 | 35609.32 | 1 | Item | 35609.32 | 35609.32 | All as order
Filtration trench (Road 3) | 1 | Item | 8094.43 | 8094.43 | 1 | Item | 8094.43 | 8094.43 | All as order
Storm Domestic Connections (Rd 4) | 1 | Item | 2175.75 | 2175.75 | 1 | Item | 2175.75 | 2175.75 | All as order
Filtration Trench Lateral (Rd 3) | 1 | Item | 473 | 473 | 1 | Item | 473 | 473 | All as order
Foul Domestic Connections (Rd 4) | 1 | Item | 2175.75 | 2175.75 | 1 | Item | 2175.75 | 2175.75 | All as order
Gullies and Connections (Rd 3 & 4) | 1 | Item | 16683.37 | 16683.37 | 1 | Item | 16683.37 | 16683.37 | All as order
Backfill Trenches With Stone | 1 | Item | 19303.22 | 19303.22 | 1 | Item | 19303.22 | 19303.22 | All as order
Removal of Surplus Excavated Material | 1 | Item | 43866.9 | 43866.9 | 1 | Item | 43866.9 | 43866.9 | All as order
Carriageway To Basecourse Over Culvert Area chainage 0-20 | 1 | Item | 15224.48 | 15224.48 | 1 | Item | 15224.48 | 15224.48 | All as order
Carriageway To Basecourse Rd 1 Chainage 20 to 72.5 | 1 | Item | 37345.61 | 37345.61 | 1 | Item | 37345.61 | 37345.61 | All as order
Carriageway To Basecourse (Rd 3) | 1 | Item | 9599.13 | 9599.13 | 1 | Item | 9599.13 | 9599.13 | All as order
Carriageway To Basecourse (Rd 4) | 1 | Item | 42433.1 | 42433.1 | 1 | Item | 42433.1 | 42433.1 | All as order
Carriageway To Basecourse - Install 2nd layer of Tarmac to road binder 80mm | 1 | Item | 67126.28 | 67126.28 | 1 | Item | 67126.28 | 67126.28 | All as order
Carriageway To completion | 1 | Item | 50695.25 | 50695.25 | 1 | Item | 50695.25 | 50695.25 | All as order
Footpaths to Binder course - Adoptable Footpath | 1 | Item | 101639.79 | 101639.79 | 1 | Item | 101639.79 | 101639.79 | All as order
Footpaths to Wearing course (min. 400m2) | 1 | Item | 25140.16 | 25140.16 | 1 | Item | 25140.16 | 25140.16 | All as order
Road Crossing Ducts | 1 | Item | 1780 | 1780 | 1 | Item | 1780 | 1780 | All as order
Roads & Sewers - Stage 3
Raising Ironwork | 1 | Item | 12500 | 12500 | 1 | Item | 7500 | 7500 | Revised allowance acceptable
CCTV & Jetting to Sewers | 1 | Item | 7500 | 7500 | 1 | Item | 7500 | 7500 | As an allowance this is acceptable
Services
Plot Connections | 70 | Plots | 2500 | 175000 | 70 | Plots | 2500 | 175000 | As an allowance this is acceptable
Diversions (Water & BT) | 2 | Item | 17500 | 35000 | 2 | Item | 17500 | 35000 | As an allowance this is acceptable
Street Lighting | 8 | Nr | 1250 | 10000 | 8 | Nr | 1250 | 10000 | As an allowance this is acceptable
Street Nameplates | 4 | Nr | 550 | 2200 | 4 | Nr | 550 | 2200 | As an allowance this is acceptable
Sub-station | 1 | Item | 65000 | 65000 | 1 | Item | 65000 | 65000 | As an allowance this is acceptable
Pumping Station | 1 | Item | 75000 | 75000 | 1 | Item | 75000 | 75000 | As an allowance this is acceptable
External Groundworks - John Mason Groundworks Order
Drainage & Soakaways | 1 | Item | 168655 | 168655 | 1 | Item | 168655 | 168655
Plot Services | 1 | Item | 24737 | 24737 | 1 | Item | 24737 | 24737
Plot Service Connections | 1 | Item | 25900 | 25900 | 1 | Item | 25900 | 25900
BT/Virgin to Footpath | 1 | Item | 20650 | 20650 | 1 | Item | 20650 | 20650
Scaffold Margin | 1 | Item | 6741 | 6741 | 1 | Item | 6741 | 6741
Parking Bays TO B/C | 1 | Item | 107336 | 107336 | 1 | Item | 107336 | 107336
Parking Bays to W/C | 1 | Item | 365579 | 365579 | 1 | Item | 365579 | 365579
Slab paths | 1 | Item | 158780 | 158780 | 1 | Item | 158780 | 158780
ASHP Base/edge/gravel | 1 | Item | 18550 | 18550 | 1 | Item | 18550 | 18550 | £265/pad; acceptable
Fence setting out | 1 | Item | 2450 | 2450 | 1 | Item | 2450 | 2450
Topsoil gardens | 1 | Item | 173055 | 173055 | 1 | Item | 122725 | 122725
Landscaping to plots | 70 | Plots | 350 | 24500 | 70 | Plots | 350 | 24500 | acceptable
Fencing to plots | 70 | Plots | 1134.29 | 79400.3 | 70 | Plots | 1134.29 | 79400.3 | Approx 14m of fence per plot; acceptable
Flag on edge retainer | 35 | m | 95 | 3325 | 35 | m | 95 | 3325
1.8m Boundary Walls | 124 | m | 350 | 43400 | 124 | m | 350 | 43400
POS Landscaping
Turfing | 2540 | m² | 7.5 | 19050 | 2540 | m² | 7.5 | 19050 | acceptable
Planting | 1 | Item | 7500 | 7500 | 1 | Item | 7500 | 7500 | Ave of £107/Plot; acceptable
Earthmoving / Muck-away
Surplus spoil to tip | 5250 |  | 27.5 | 144375 | 5250 |  | 27.5 |  | This site is a 'Fill' site and no supporting information have been provided to justify the applicants claim. This is our final position
Muck management on-site | 1 | Sum | 25000 | 25000 | 1 | Sum | 25000 | 25000 | Subject to demostrating soil removal is required
|  |  | Sub-Total | 3624316.85 |  |  | Sub-Total | 3035311.85
Preliminaries |  |  |  | 1140162 |  |  |  | 848432
|  |  | Total | 13007830.53 |  |  | Total | 11808992.165

## Preliminaries
Site Labour | Nr | Weeks | % | Total | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total |  | Total | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total
Site Manager | 1 | 110 | 100 | 110 | Weeks | 1635 |  | 179850 |  |  |  | 179850 |  | 110 | Weeks | 1635 |  | 179850 |  |  |  | 179850
Assistant Site Manaqer | 1 | 110 | 100 | 110 | Weeks | 1154 |  | 126940 |  |  |  | 126940 |  | 70 | Weeks | 1154 |  | 80780 |  |  |  | 80780 |  | Not required from day one
General labourer | 1 | 110 | 100 | 110 | Weeks | 650 |  | 71500 |  |  |  | 71500 |  | 110 | Weeks | 650 |  | 71500 |  |  |  | 71500
Gateman | 1 | 110 | 100 | 110 | Weeks | 650 |  | 71500 |  |  |  | 71500 |  | 110 | Weeks | 650 | [5 empty] | 0 |  | Not required, the project isnt large enough
Fork lift driver | 1 | 110 | 100 | 110 | Weeks | 966 |  | 106260 |  |  |  | 106260 |  | 90 | Weeks | 966 |  | 86940 |  |  |  | 86940 |  | not required for entire duration
Enqineer | 1 | 110 | 25 | 27.5 | Weeks | 1500 |  | 41250 |  |  |  | 41250 |  | 11 | Weeks | 1500 |  | 16500 |  |  |  | 16500 |  | 10% of duration
Design Co-ordinator | 1 | 110 | 25 | 27.5 | Weeks | 1264 |  | 34760 |  |  |  | 34760 |  | 27.5 | Weeks | 1264 |  | 34760 |  |  |  | 34760
Site Labour Totals | [12 empty] | 632060 | [9 empty] | 470330 | 161730
Site Compound & Set Up |  |  |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total
Tools & Tackle |  |  |  | 110 | weeks | 300 | 33000 |  |  |  |  | 33000 |  | 110 | weeks | 100 | 11000 |  |  |  |  | 11000 |  | Excessive
Signage |  |  |  | 1 | item | 3000 | 3000 |  |  |  |  | 3000 |  | 1 | item | 3000 | 3000 |  |  |  |  | 3000
Tree protection fencing Herras Fencing |  |  |  | 0 | m | [6 empty] | 0 |  | 0 | m | [6 empty] | 0
Herras Fencing |  |  |  | 700 | m | 17.5 | 7000 | 5250 |  |  |  | 12250 |  | 700 | m | 17.5 | 7000 | 5250 |  |  |  | 12250
Pedestrian Barriers |  |  |  | 1 | item | 2000 | 1500 | 500 |  |  |  | 2000 |  | 1 | item | 2000 | 1500 | 500 |  |  |  | 2000
Gate |  |  |  | 1 | nr | 750 |  |  |  | 750 |  | 750 |  | 1 | nr | 750 |  |  |  | 750 |  | 750
Temporary Haul Roads |  |  |  | 750 | m² | 940 | 4320 | 2727 |  |  |  | 7047 |  | 750 | m² |  | 4320 | 2727 |  |  |  | 7047 |  | Rate is incorrect but doesn’t seem to carry through
Site pedestrian access paths |  |  |  | 1 | item | 2349 | 1440 | 909 |  |  |  | 2349 |  | 1 | item | 2349 | 1440 | 909 |  |  |  | 2349
Hardcore to compound |  |  |  | 1500 | m² | 6.26 | 5760 | 3636 |  |  |  | 9396 |  | 1500 | m² | 6.26 | 5760 | 3636 |  |  |  | 9396
Tarmac base course |  |  |  | 750 | m² | 12.3 | 1728 | 7500 |  |  |  | 9228 |  | 750 | m² | 12.3 | 1728 | 7500 |  |  |  | 9228
Timber Edgings |  |  |  | 800 | m | 10.04 | 330 | 975 |  |  |  | 1305 |  | 800 | m | 10.04 | 330 | 975 |  |  |  | 1305
Compound fence |  |  |  | 200 | fn | 95 |  |  |  | 19000 |  | 19000 |  | 200 | fn | 95 |  |  |  | 19000 |  | 19000 |  | Can you provide photos that demonstrate this was installed?
Pedestrian gate |  |  |  | 2 | nr | 350 |  |  |  | 700 |  | 700 |  | 2 | nr | 350 |  |  |  | 700 |  | 700
Compound gate |  |  |  | 1 | nr | 1500 |  |  |  | 1500 |  | 1500 |  | 1 | nr | 1500 |  |  |  | 1500 |  | 1500
Cloud pass/office setup & turnstile |  |  |  | 1 | nr | 7000 |  |  |  | 7000 |  | 7000 |  | 1 | nr | 7000 |  |  |  | 7000 |  | 7000 |  | Can you provide photos that demonstrate this was installed?
Clear site on completion |  |  |  | 1 | item | 2500 |  | 2500 |  |  |  | 2500 |  | 1 | item | 2500 |  | 2500 |  |  |  | 2500
Concrete base for silo |  |  |  | 1 | item | 1167 | 717 | 450 |  |  |  | 1167 |  | 1 | item | 1167 | 717 | 450 |  |  |  | 1167
Groundworks to compound |  |  |  | 1 | item | 5000 |  |  |  | 5000 |  | 5000 |  | 1 | item | 5000 |  |  |  | 5000 |  | 5000
Subcontractor compound |  |  |  | 1 | item | 5000 |  |  |  | 5000 |  | 5000 |  | 1 | item | 5000 |  |  |  | 5000 |  | 5000 |  | Can you provide photos that demonstrate this was installed? A separate compound for S/C's ona site this side seems overkill
Site Compound & Set-up Totals | [12 empty] | 122192 | [9 empty] | 100192 | 22000
Accommodation |  |  |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total
24ft Office (Entrance) |  |  |  | 1 | 110 | 58 |  |  | 6380 |  |  | 6380 |  | 1 | 110 | 58 |  |  | 6380 |  |  | 6380
32flOffice |  |  |  | 1 | 110 | 58 |  |  | 6380 |  |  | 6380 |  | 1 | 110 | 58 |  |  | 6380 |  |  | 6380
32ft Canteen |  |  |  | 1 | 110 | 58 |  |  | 6380 |  |  | 6380 |  | 1 | 110 | 58 |  |  | 6380 |  |  | 6380
20ft Drvinq Room |  |  |  | 1 | 110 | 52 |  |  | 5720 |  |  | 5720 |  | 1 | 110 | 52 |  |  | 5720 |  |  | 5720
24ft Toilet Block |  |  |  | 1 | 110 | 60 |  |  | 6600 |  |  | 6600 |  | 1 | 110 | 60 |  |  | 6600 |  |  | 6600
20ft Store |  |  |  | 2 | 110 | 45 |  |  | 9900 |  |  | 9900 |  | 2 | 110 | 45 |  |  | 9900 |  |  | 9900
Staircase |  |  |  | 1 | 110 | 25 |  |  | 2750 |  |  | 2750 |  | 1 | 110 | 25 |  |  | 2750 |  |  | 2750
Scaffold for qantrvs |  |  |  | 2 | 1 | 2000 |  |  | 4000 |  |  | 4000 |  | 2 | 1 | 2000 |  |  | 4000 |  |  | 4000
Scaffold platform to stores |  |  |  | 1 | 1 | 2000 |  |  | 2000 |  |  | 2000 |  | 1 | 1 | 2000 |  |  | 2000 |  |  | 2000
Furniture & IT |  |  |  | 1 | 1 | 4000 |  |  | 4000 |  |  | 4000 |  | 1 | 1 | 4000 |  |  | 4000 |  |  | 4000
Carriaqe to / from site |  |  |  | 16 | 1 | 400 |  |  | 6400 |  |  | 6400 |  | 16 | 1 | 75 |  |  | 1200 |  |  | 1200 |  | £400 each way? This is very high
Septic Tank Empties |  |  |  | 1 | 20 | 250 |  |  | 5000 |  |  | 5000 |  | 1 | 20 | 250 |  |  | 5000 |  |  | 5000
CleaninQ cabins |  |  |  | 1 | 120 | 120 |  |  | 14400 |  |  | 14400 |  | 1 | 110 | 120 |  |  | 13200 |  |  | 13200 |  | why 120?
[13 empty] | 79910 | [9 empty] | 73510 | 6400
Security |  |  |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total
Security Cameras |  |  |  | 110 | weeks | 300 |  |  |  | 33000 |  | 33000 |  | 110 | weeks | 175 |  |  |  | 19250 |  | 19250 |  | Rate is high, please provide evidence?
CCTV Install |  |  |  | 1 | nr | 4000 |  |  |  | 4000 |  | 4000 |  | 1 | nr | 0 |  |  |  | 0 |  | 0 |  | This is included in the rate above
Security Totals | [12 empty] | 37000 | [9 empty] | 19250 | 17750
Temporary Works |  |  |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total
Skips Artstone Protection Plastic Suraeon Allowance |  |  |  | 280 | nr | 270 |  |  |  | 75600 |  | 75600 |  | 110 | nr | 270 |  |  |  | 29700 |  | 29700 |  | 2.5 skips per week is excessive
Arstone Protection |  |  |  | 70 | nr | 30 | 2100 |  |  |  |  | 2100 |  | 70 | nr | 30 | 0 |  |  |  |  | 0 |  | what is this?
Plastic Surgeon Allowance |  |  |  | 70 | nr | 50 |  |  |  | 3500 |  | 3500 |  | 70 | nr | 50 |  |  |  | 0 |  | 0 |  | this is a risk item, which should be accounted for from your contingency risk allowance
Temporary Works Total | [12 empty] | 81200 | [9 empty] | 29700 | 51500
Plant |  |  |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total
Road Sweeper/Wheel Wash |  |  |  | 1 | Visit | 7500 |  |  | 7500 |  |  | 7500 |  | 1 | Visit | 7500 |  |  | 7500 |  |  | 7500
12.Sm Telehandler |  |  |  | 104 | weeks | 400 |  |  | 41600 |  |  | 41600 |  | 90 | weeks | 400 |  |  | 36000 |  |  | 36000 |  | wont need for the first 15 weeks or last 5 weeks
Fuel |  |  |  | 104 | weeks | 400 |  |  | 41600 |  |  | 41600 |  | 90 | weeks | 400 |  |  | 36000 |  |  | 36000
Fuel Bowser |  |  |  | 104 | weeks | 25 |  |  | 2600 |  |  | 2600 |  | 90 | weeks | 25 |  |  | 2250 |  |  | 2250
Punctures & Repairs |  |  |  | 104 | weeks | 50 |  |  | 5200 |  |  | 5200 |  | 90 | weeks | 50 |  |  | 4500 |  |  | 4500
Crane 35T - Contract Lift - Full Day |  |  |  | 23 | Visit | 900 |  |  | 20700 |  |  | 20700 |  | 23 | Visit | 900 |  |  | 20700 |  |  | 20700
Generator /incl. fuel) |  |  |  | 4 | weeks | 1200 |  |  | 4800 |  |  | 4800 |  | 4 | weeks | 250 |  |  | 1000 |  |  | 1000 |  | excessive
Plant Total | [12 empty] | 124000 | [9 empty] | 107950 | 16050
Temporary Services |  |  |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total
Electrical Connection to compound |  |  |  | 1 | item | 6500 |  |  |  | 6500 |  | 6500 |  | 1 | item | 2000 |  |  |  | 2000 |  | 2000 |  | TBS is typically £1500
Electric use |  |  |  | 110 | weeks | 250 |  |  |  |  | 27500 | 27500 |  | 110 | weeks | 150 |  |  |  |  | 16500 | 16500 |  | Rate and duration excessive
Meter Cabinet |  |  |  | 1 | nr | 500 | 250 | 250 |  |  |  | 500 |  | 1 | nr | 500 | 250 | 250 |  |  |  | 500
Water Connection to Compound |  |  |  | 1 | nr | 2000 |  |  |  | 2000 |  | 2000 |  | 1 | nr | 1000 |  |  |  | 2000 |  | 2000 |  | excessive
Weekly use |  |  |  | 110 | weeks | 40 |  |  |  |  | 4400 | 4400 |  | 110 | weeks | 40 |  |  |  |  | 4400 | 4400
Plant Total | [12 empty] | 40900 | [9 empty] | 25400 | 15500
Sundries |  |  |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total |  | Quantity | Unit | Rate | Materials | Labour | Plant | S/C | Services | Total
Post Completion Drain iettinq/CCTV |  |  |  | 1 | nr | 100 |  |  |  | 100 |  | 100 |  | 1 | nr | 100 |  |  |  | 100 |  | 100
Temporary Lightinq |  |  |  | 1 | nr | 1000 |  |  | 1000 |  |  | 1000 |  | 1 | nr | 1000 |  |  | 1000 |  |  | 1000
Fire Alarm |  |  |  | 2 | nr | 500 |  |  |  | 1000 |  | 1000 |  | 2 | nr | 100 |  |  |  | 200 |  | 200 |  | excessive
Health & Safety Visits |  |  |  | 26 | months | 800 |  |  |  | 20800 |  | 20800 |  | 26 | months | 800 |  |  |  | 20800 |  | 20800
Sundries Total | [12 empty] | 22900 | [9 empty] | 22100 | 800
[13 empty] | 1140162 | [9 empty] | 848432 | 291730
291730